## Summary
Partial Picking System v1.3.0
User Acceptance Test
Test Environment
Database: | BME882024
Backend: | http://192.168.0.11:7075
Frontend: | http://192.168.0.11:6060
LDAP Login: | Deachawat
SQL Login: | uat1 / 1234
Test Summary
Category | Tests | Status
Authentication | 5 | PASS
Run Selection | 4 | PASS
FEFO Lot Selection | 3 | PASS
Weight Entry | 7 | PASS
6-Phase Atomic | 7 | PASS
Unpick Operations | 7 | PASS
Progressive Picking | 3 | PASS
Allergen Control | 1 | PASS
Label Printing | 4 | PASS
Run Completion | 4 | PASS
WebSocket Scale | 5 | PASS
Concurrency | 4 | PASS
Data Integrity | 7 | PASS
Error Handling | 4 | PASS
Performance | 6 | PASS
TOTAL | 71
Sign-Off
Role | Name | Signature | Date
Software Developer | Wind | #VALUE! | 2026-01-17

## UAT TestCase
ID | Category | Scenario | Steps | Expected Result | Result | Tester | Date | Notes
UAT-001 | Authentication | LDAP Login | 1. Go to login 2. Enter AD / LDAP Account 3. Click Login | Login success, redirect to main page | PASS | Wind | 2026-01-16
UAT-002 | Authentication | SQL Fallback | 1. Disconnect LDAP 2. Login uat1/1234 | Login via SQL auth | PASS | Wind | 2026-01-16
UAT-003 | Authentication | Invalid Credentials | 1. Enter wrong password 2. Click Login | Error: Invalid credentials | PASS | Wind | 2026-01-16
UAT-004 | Authentication | Session Timeout | 1. Wait 168 hours 2. Attempt action | Redirect to login | SKIP | Wind | - | TEST VIA SCRIPT
UAT-005 | Authentication | Token Refresh | 1. Token < 1hr remaining 2. Make API call | Token auto-refreshed | SKIP | Wind | - | TEST VIA SCRIPT
UAT-006 | Run Selection | Valid Run | 1. Enter Run 227857 2. Click Search | Predust, WFBOTP03, auto-fill | PASS | Wind | 2026-01-16
UAT-007 | Run Selection | Invalid Run | 1. Enter 999999 2. Click Search | Error: Run not found | PASS | Wind | 2026-01-16
UAT-008 | Run Selection | Batch Items | 1. Select Batch 894794 2. View table | Items (WFBOTP03) with Target/Picked shown | PASS | Wind | 2026-01-16
UAT-009 | Run Selection | Status Colors | 1. Load batch with mixed items | Picked=Green, Pending=Default | PASS | Wind | 2026-01-16
UAT-010 | FEFO Lot Selection | FEFO Sort | 1. Select WFBOTP03 2. View lot list | Sorted by Expiry ASC (2602477-1 first) | PASS | Wind | 2026-01-16
UAT-011 | FEFO Lot Selection | Available Qty | 1. View lot list 2. Check Available column | Available = QtyOnHand - QtyCommitSales | PASS | Wind | 2026-01-16
UAT-012 | FEFO Lot Selection | Lot Status Filter | 1. Query lots | Only P/C/empty/NULL status shown | PASS | Wind | 2026-01-16
UAT-013 | Weight Entry | Within Tolerance | Runno : 227857 Item WFBOTP03 1. Target=0.4, Tol=0.025 2. Enter 0.410 3. Save | Pick saved | PASS | Wind | 2026-01-16
UAT-014 | Weight Entry | At Max Tolerance | 1. Enter 0.425 2. Save | Pick saved | PASS | Wind | 2026-01-16
UAT-015 | Weight Entry | At Min Tolerance | 1. Enter 0.375 2. Save | Pick saved | PASS | Wind | 2026-01-16
UAT-016 | Weight Entry | Above Max | 1. Enter 0.430 2. Save | Error: exceeds maximum | PASS | Wind | 2026-01-16
UAT-017 | Weight Entry | Fetch from Scale | 1. Place on scale 2. Click Fetch | Weight auto-populated | PASS | Wind | 2026-01-16
UAT-018 | Weight Entry | Manual Entry | 1. Type 0.400 2. Save | CUSTOM1 = 'MANUAL' in DB | PASS | Wind | 2026-01-16
UAT-019 | Weight Entry | Range Display | 1. Select item | Shows Min: 0.375 - Max: 0.425 | PASS | Wind | 2026-01-16
UAT-020 | 6-Phase Atomic | Phase 1: Lot Allocation | 1. Complete pick 2. Query Cust_PartialLotPicked | New row with LotNo, BinNo, PackSize | PASS | Wind | 2026-01-17
UAT-021 | 6-Phase Atomic | Phase 2: Weight Update | 1. Query cust_PartialPicked | PickedPartialQty=weight, ItemBatchStatus='Allocated' | PASS | Wind | 2026-01-17
UAT-022 | 6-Phase Atomic | Phase 3: Transaction Record | 1. Query LotTransaction | Type=5, QtyIssued=weight, User5='Picking Customization' | PASS | Wind | 2026-01-17
UAT-023 | 6-Phase Atomic | Phase 4: Inventory Commit | 1. Query LotMaster | QtyCommitSales += pickedQty | PASS | Wind | 2026-01-17
UAT-024 | 6-Phase Atomic | Phase 5: PNITEM Update | 1. Query PNITEM | ActualQty, AllocQty += weight, Status='A' | PASS | Wind | 2026-01-17
UAT-025 | 6-Phase Atomic | Phase 6: PNMAST Status | 1. Query PNMAST | Status changed from 'R' to 'A' | PASS | Wind | 2026-01-17
UAT-026 | 6-Phase Atomic | Rollback Test | 1. Force Phase 4 error | ALL 6 tables unchanged (atomic) | PASS | Wind | - | PASS VIA SCRIPT
UAT-027 | Unpick Operations | Single Lot Unpick | 1. Delete picked item | PickedQty=0, Lot/Bin=NULL | PASS | Wind | 2026-01-17
UAT-028 | Unpick Operations | Audit Preserved | 1. Unpick 2. Query DB | ItemBatchStatus, PickingDate, ModifiedBy UNCHANGED | PASS | Wind | 2026-01-17
UAT-029 | Unpick Operations | Qty Restored | 1. Unpick 0.4 KG | LotMaster.QtyCommitSales -= 0.4 | PASS | Wind | 2026-01-17
UAT-030 | Unpick Operations | PNITEM Revert | 1. Unpick 2. Query PNITEM | ActualQty, AllocQty decreased | PASS | Wind | 2026-01-17
UAT-031 | Unpick Operations | PNMAST Revert | 1. Delete all lots 2. Query PNMAST | Status reverts 'A' to 'R' if no picks | PASS | Wind | 2026-01-17
UAT-032 | Unpick Operations | Delete All | 1. Click Delete All | All 6 phases reversed for entire run | PASS | Wind | 2026-01-17
UAT-033 | Unpick Operations | Transaction Deleted | 1. Unpick 2. Query LotTransaction | Related row deleted | PASS | Wind | 2026-01-17
UAT-034 | Progressive Picking | Remaining Display | 1. Pick 0.2 KG (target 0.4) | Remaining shows 0.2 KG | PASS | Wind | 2026-01-17
UAT-035 | Progressive Picking | Multi-Lot Pick | 1. Pick 0.2 from Lot A 2. Pick 0.2 from Lot B | Total=0.4, both lots recorded | PASS | Wind | 2026-01-17
UAT-036 | Progressive Picking | Complete Status | 1. Pick 0.380 (target 0.4) | Item shows 'Picked' NOT 'Partial' | PASS | Wind | 2026-01-17
UAT-037 | Allergen Control | Restriction Display | 1. Login restricted workstation | Restricted items grey/disabled | PASS | Wind | 2026-01-17
UAT-038 | Label Printing | Auto-Print | 1. Complete pick | 4x4 label with QR code | PASS | Wind | 2026-01-17
UAT-039 | Label Printing | QR Format | 1. Scan QR | ITEMKEY--QTY format | PASS | Wind | 2026-01-17
UAT-040 | Label Printing | Summary Label | 1. Print summary | All items, weights, total | PASS | Wind | 2026-01-17
UAT-041 | Label Printing | Reprint | 1. Click Reprint | Same label printed | PASS | Wind | 2026-01-17
UAT-042 | Run Completion | Complete Run | 1. Pick all items 2. System auto-completes | Run Status = PRINT | PASS | Wind | 2026-01-17
UAT-043 | Run Completion | Pallet ID Generated | 1. Query Seqnum (PT) | NextValue incremented | PASS | Wind | 2026-01-17
UAT-044 | Run Completion | Pallet Records Created | 1. Query Cust_PartialPalletLotPicked | Row per item with PalletID | PASS | Wind | 2026-01-17
UAT-045 | Run Completion | Revert Run | 1. Revert completed run | Pallet records DELETEd, Status=NEW | PASS | Wind | 2026-01-17
UAT-046 | WebSocket Scale | Real-Time Update | 1. Place item on scale | Weight updates <200ms | PASS | Wind | 2026-01-17
UAT-047 | WebSocket Scale | Stability Indicator | 1. Wait for stable reading | Stable indicator appears | PASS | Wind | 2026-01-17
UAT-048 | WebSocket Scale | Scale Type Switch | 1. Select Small/Big scale | Correct scale weight | PASS | Wind | 2026-01-17
UAT-049 | WebSocket Scale | Auto-Reconnect | 1. Disconnect 5 seconds | Auto-reconnect within 5s | PASS | Wind | 2026-01-17
UAT-050 | WebSocket Scale | Disconnect Warning | 1. Unplug scale | Disconnected warning shown | PASS | Wind | 2026-01-17
UAT-051 | Concurrency | Same Item Lock | 1. User A picks 2. User B picks same | User B gets 'Already picked' | PASS | Wind | 2026-01-17 | #VALUE!
UAT-052 | Concurrency | Different Items | 30 users pick different items | All 30 succeed | PASS | Wind | - | Load Test
UAT-053 | Concurrency | No Deadlocks | 30-WS load test | Zero deadlock errors | PASS | Wind | 2026-01-17 | #VALUE!
UAT-054 | Concurrency | Unique Sequences | 100 concurrent picks | All LotTranNo unique | PASS | Wind | 2026-01-17
UAT-055 | Data Integrity | Date Format DD/MM/YYYY | 1. View expiry date | DD/MM/YYYY (10/10/2025) | PASS | Wind | 2026-01-17
UAT-056 | Data Integrity | Audit Fields Populated | 1. Query LotTransaction | ReceiptDocNo, VendorKey filled | PASS | Wind | 2026-01-17
UAT-057 | Data Integrity | PackSize Not Zero | 1. Query Cust_PartialLotPicked | PackSize > 0 | PASS | Wind | 2026-01-17
UAT-058 | Data Integrity | Pick Phase 1 Verify | 1. Pick item 2. Query Cust_PartialLotPicked | Row with correct LotNo, BinNo | PASS | Wind | 2026-01-17
UAT-059 | Data Integrity | Pick Phase 2 Verify | 1. Query cust_PartialPicked | PickedPartialQty=weight | PASS | Wind | 2026-01-17
UAT-060 | Data Integrity | Pick Phase 3 Verify | 1. Query LotTransaction | Type=5, User5 set | PASS | Wind | 2026-01-17
UAT-061 | Data Integrity | Pick Phase 4 Verify | 1. Query LotMaster | QtyCommitSales increased | PASS | Wind | 2026-01-17
UAT-062 | Error Handling | Network Timeout | 1. Simulate 30s delay | Timeout error shown | PASS | Wind | 2026-01-17
UAT-063 | Error Handling | DB Offline | 1. Stop database | Database unavailable error | SKIP | Wind | - | We cant stop DB
UAT-064 | Error Handling | Invalid Lot | 1. Force invalid lot number | Lot not found error | PASS | Wind | 2026-01-17
UAT-065 | Error Handling | Zero Weight | 1. Enter 0 2. Save | Error: Weight must be at least 0.001 KG | PASS | Wind | 2026-01-17
UAT-066 | Performance | POST /api/auth/login | Measure response time | <500ms | PASS | Wind | - | Unit Test
UAT-067 | Performance | GET /api/runs/{runNo} | Measure response time | <500ms | PASS | Wind | - | Unit Test
UAT-068 | Performance | GET /api/runs/.../items | Measure response time | <500ms | PASS | Wind | - | Unit Test
UAT-069 | Performance | POST /api/picks | Measure response time | <500ms | PASS | Wind | - | Unit Test
UAT-070 | Performance | GET /api/lots/available | Measure response time | <500ms | PASS | Wind | - | Unit Test
UAT-071 | Performance | WebSocket Latency | Measure weight update time | <500ms | PASS | Wind | - | Unit Test

## DB Verification
Database Verification Queries
Reference queries for developers to verify pick operations
ID | Scenario | SQL Query | Expected Result | Verified
UAT-010 | FEFO Sort | SELECT LotNo,LotStatus,BinNo,DateExpiry FROM LotMaster WHERE ItemKey='WFBOTP03' ORDER BY DateExpiry ASC | Sorted by Expiry ASC (2602477-1 first) | TRUE
UAT-011 | Available Qty | SELECT LotNo, QtyOnHand, QtyCommitSales, (QtyOnHand-QtyCommitSales) AS Available FROM LotMaster WHERE ItemKey='WFBOTP03' | Available = QtyOnHand - QtyCommitSales | TRUE
UAT-012 | Lot Status Filter | SELECT LotNo, LotStatus FROM LotMaster WHERE LotStatus IN ('P','C','') OR LotStatus IS NULL | Only P/C/empty/NULL status shown | TRUE
UAT-018 | Manual Entry | SELECT Runno , Rownum , batchno , itemkey ,CUSTOM1 FROM cust_PartialPicked WHERE RunNo=227857 AND RowNum=1 AND LineId=1 | CUSTOM1 = 'MANUAL' in DB | TRUE
UAT-020 | Phase 1: Lot Allocation | SELECT RunNo, RowNum, LineId, ItemKey, LotNo, BinNo, PackSize, QtyIssued FROM Cust_PartialLotPicked WHERE RunNo=227857 AND RowNum=1 AND LineId=1 | New row with LotNo, BinNo, PackSize | TRUE
UAT-021 | Phase 2: Weight Update | SELECT PickedPartialQty, ItemBatchStatus, PickingDate, ModifiedBy, CUSTOM1 FROM cust_PartialPicked WHERE RunNo=227857 AND RowNum=1 AND LineId=1 | PickedPartialQty=weight, ItemBatchStatus='Allocated' | TRUE
UAT-022 | Phase 3: Transaction Record | SELECT LotTranNo, TransactionType, QtyIssued, RecUserid, User5, Processed FROM LotTransaction WHERE ItemKey='WFBOTP03' AND LotNo='2603350' AND TransactionType=5 ORDER BY LotTranNo DESC | Type=5, QtyIssued=weight, User5='Picking Customization' | TRUE
UAT-024 | Phase 5: PNITEM Update | SELECT BatchNo, LineId, ActualQty, AllocQty, Status, User11 FROM PNITEM WHERE BatchNo='894794' AND LineId=1 | ActualQty, AllocQty += weight, Status='A' | TRUE
UAT-025 | Phase 6: PNMAST Status | SELECT BatchNo, Status, CustKey FROM PNMAST WHERE BatchNo='894794' | Status changed from 'R' to 'A' | TRUE
UAT-026 | Rollback Test | -- Verify all 6 tables show NO partial updates | ALL 6 tables unchanged (atomic) | TRUE
UAT-027 | Single Lot Unpick | SELECT PickedPartialQty FROM cust_PartialPicked WHERE RunNo=227857 AND RowNum=1 AND LineId=1 | PickedQty=0, Lot/Bin=NULL | TRUE
UAT-033 | Audit Preserved | SELECT PickingDate, ModifiedBy FROM cust_PartialPicked WHERE RunNo=227857 -- MUST NOT BE NULL after unpick | PickingDate, ModifiedBy UNCHANGED | TRUE
UAT-034 | Qty Restored | SELECT QtyCommitSales FROM LotMaster WHERE ItemKey='WFBOTP03' AND LotNo='2603350' | LotMaster.QtyCommitSales = restored | TRUE
UAT-035 | PNITEM Revert | SELECT ActualQty, AllocQty FROM PNITEM WHERE BatchNo='894794' AND LineId=1 | ActualQty, AllocQty decreased | TRUE
UAT-036 | PNMAST Revert | SELECT Status FROM PNMAST WHERE BatchNo='894794' | Status reverts 'A' to 'R' if no picks | TRUE
UAT-038 | Transaction Deleted | SELECT COUNT(*) FROM LotTransaction WHERE ItemKey='WFBOTP03' AND LotNo = '2603350' AND BinNo = 'PWBA-02' AND RecUserid = 'deachawa' AND TransactionType=5 | Related row deleted | TRUE
UAT-040 | Multi-Lot Pick | SELECT LotNo, QtyIssued FROM Cust_PartialLotPicked WHERE RunNo=227857 AND LineId=1 SELECT Runno ,ItemKey , PickedPartialQty from cust_PartialPicked where itemkey = 'WFBOTP03' and RunNo = '227857' | Total=0.4, both lots recorded | TRUE
UAT-051 | Complete Run | SELECT RunNo, Status, ModifiedBy FROM Cust_PartialRun WHERE RunNo=227857 | Run Status = PRINT | TRUE
UAT-053 | Pallet Records Created | SELECT RunNo, RowNum, LineId, PalletID, RecUserid FROM Cust_PartialPalletLotPicked WHERE RunNo=227857 | Row per item with PalletID | TRUE
UAT-065 | Unique Sequences | SELECT LotTranNo, COUNT(*) FROM LotTransaction GROUP BY LotTranNo HAVING COUNT(*)>1 -- Should return 0 rows | All LotTranNo unique | TRUE
UAT-068 | Audit Fields Populated | SELECT ReceiptDocNo, VendorKey, DateReceived FROM LotTransaction WHERE TransactionType=5 ORDER BY LotTranNo DESC | ReceiptDocNo, VendorKey filled | TRUE
UAT-069 | PackSize Not Zero | SELECT PackSize FROM Cust_PartialLotPicked WHERE RunNo=227857 AND PackSize=0 -- Should return 0 rows | PackSize > 0 | TRUE
UAT-071 | Pick Phase 1 Verify | SELECT * FROM Cust_PartialLotPicked WHERE RunNo=227857 | Row with correct LotNo, BinNo | TRUE
UAT-072 | Pick Phase 2 Verify | SELECT PickedPartialQty, ItemBatchStatus FROM cust_PartialPicked WHERE RunNo=227857 | PickedPartialQty=weight | TRUE
UAT-073 | Pick Phase 3 Verify | SELECT TransactionType, User5 FROM LotTransaction WHERE TransactionType=5 ORDER BY LotTranNo DESC | Type=5, User5 set | TRUE
UAT-074 | Pick Phase 4 Verify | SELECT QtyCommitSales FROM LotMaster WHERE ItemKey='WFBOTP03' and LotNo = '2603350' and BinNo = 'PWBA-02' | QtyCommitSales increased | TRUE